## Test Scenarios
Project Name | Bugasura
Reference Document | Application URL
Created By | Huma Sinha
Creation Date | Sep 12th, 2024
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
Login | Application URL | Verify the working of Login functionality |  | 16
Project | Application URL | Verify the working of Project Functionality |  | 14
What's New | Application URL | Verify the working of What's New functionality |  | 1
Manage | Application URL | Verify the working of Manage functionality |  | 11

## Login
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
TC_LF_001 | (TS_001) Login Functionality | Validate the presence and visibility of all elements on the login page. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the login page URL. Verify that the login page contains the following UI elements: Username/email field Password field Login button Forgot Password link Sign-In link/button Check if all elements are visible. | Not Applicable | All the mentioned elements should be present and visible on the login page. | All the mentioned elements are present and visible on the login page. |  | Pass
TC_LF_002 | (TS_001) Login Functionality | Validate that the user can log in with valid credentials. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the login page. Enter a valid username/email in the username field. Enter a valid password in the password field. Click the "Login" button. | Email Address - sudhaamirita@gmail.com Password - 12345 | User should be successfully logged in and redirected to the homepage/Project. | User is successfully logged in and redirected to the homepage/Project. |  | Pass
TC_LF_003 | (TS_001) Login Functionality | Verify error message is displayed for invalid login credentials. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the login page. Enter an invalid email in the email field. Enter an incorrect password. Click the "Login" button. | Email Address - pqrsbudna@gmail.com Password -olm@12 | 1.Login should fail. 2."Email I'D doesn't exists" - message should pop up. | 1.Login fails. 2. An appropriate error message (e.g, "Email I'D doesn't exists") is displayed. |  | Pass
TC_LF_004 | (TS_001) Login Functionality | Validate the Forgot Password functionality. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Enter the registered email address. 3. Click on "Forgot Password" link 4.Enter email in Reset Password page 5.Click "Submit" button. | Enter registered email id | 1. Password reset email should be sent to the registered email address. 2. User should be prompted with a success message. | 1. Password reset email is sent to the registered email address. 2. User is prompted with a success message. |  | Pass
TC_LF_006 | (TS_001) Login Functionality | Validate the error message when both username and password fields are left empty. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Leave both the username and password fields empty. 3.Click the "Login" button. | Not Applicable | Error message should be displayed, e.g., "Username and password cannot be empty." | Error message is displayed, e.g, "Email and Password is required" |  | Pass
TC_LF_007 | (TS_001) Login Functionality | Verify the validation for incorrect email format in the username field. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Enter an invalid email format in the username field 3.Enter any valid/invalid password. 4.Click on the "Login" button. | Email : mehragmail.234com mehra@123 | System should show a validation message, e.g., "Please enter a valid email id." | System shows a validation message, e.g., "Please enter a valid email id" |  | Pass
TC_LF_008 | (TS_001) Login Functionality | Verify if the "Login" button is disabled until both fields are filled. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Keep one of the fields (either username or password) empty. 3.Try to click the "Login" button. | Not Applicable | "Login" button should remain disabled until both username and password fields are filled. | "Login" button remains disabled until both username and password fields are filled. |  | Pass
TC_LF_009 | (TS_001) Login Functionality | Verify that the password field masks the input. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Enter any valid or invalid password in the password field. 3.Observe the field for visibility of the characters. | Not Applicable | Password field should display characters as dots or asterisks, not plain text. | Password field displays characters as dots, not plain text. |  | Pass
TC_LF_010 | (TS_001) Login Functionality | Verify that the login can be submitted by pressing the Enter key. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Enter any valid username and password. 3.Press the "Enter" key on the keyboard instead of clicking the "Login" button. | Not Applicable | User should be successfully logged in after pressing the "Enter" key. | User is successfully logged in after pressing the "Enter" key. |  | Pass
TC_LF_011 | (TS_001) Login Functionality | Verify that the password field enforces a minimum character limit. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2. Enter valid email id 3.Enter a password that is shorter than the minimum required length (e.g, 4 characters). 4.Try to log in by clicking the "Login" button. | Password: 1234 | System should show an error message, Not too short! enter min 5 characters. | System shows an error message, e.g., "Not too short! enter min 5 characters." |  | Pass
TC_LF_012 | (TS_001) Login Functionality | Verify account creation/sign up with invalid email id | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Click on "Create a Account" 3.Enter invalid email id and password 4. Click on Submit button. | Email Id : qqrtsi@gmail.com | 1.System should display an error message stating that the email ID does not exist. 2.User should not be allowed to proceed with invalid credentials. | 1.System does not display an error and proceeds with the invalid details. 2. After account creation, a pop-up appears with the message: 'Your email ************@gmail.com has been bouncing. We will need to verify your email to continue. |  | Pass
TC_LF_013 | (TS_001) Login Functionality | Verify error messages do not reveal whether the email or password is incorrect. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.Enter a correct username but incorrect password. 3.Attempt to log in. 4.Repeat with incorrect username and correct password. |  | System should display a generic error message like "Invalid Credentials" to avoid revealing which field is wrong for security reasons. | System displays a generic error message like "Invalid Credentials" to avoid revealing which field is wrong for security reasons. |  | Pass
TC_LF_014 | (TS_001) Login Functionality | Validate the presence and visibility of all elements on the login page. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the login page. Verify that the login page contains the following UI elements: Welcome message: "Welcome to Bugasura" Google Sign-In button Email field Sign In button for email login "Sign in with Email" option | Not Applicable | All elements should be present and clearly visible on the page. | All elements are present and clearly visible on the page. |  | Pass
TC_LF_015 | (TS_001) Login Functionality | Validate that the Google Sign-In button redirects to the Google authentication page. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.On the login page, click the "Google Sign-In" button. 3.Verify if the user is redirected to the Google sign-in page. | Not Applicable | System should redirect the user to the Google authentication page, where the user can sign in with their Google credentials. | System redirects the user to the Google authentication page, where the user can sign in with their Google credentials. |  | Pass
TC_LF_016 | (TS_001) Login Functionality | Validate that a user can successfully log in using Google credentials. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2.On the login page, click the "Google Sign-In" button. 3.Enter valid Google credentials. | Not Applicable | User should successfully log in and be redirected to the Bugasura Project. | User is successfully log in and redirected to the Bugasura Project. |  | Pass

## Projects
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
TC_DF_001 | TS_002 Project Functionality | Validate search functionality in Projects | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar | Search : Bugasura Live Support | Bugasura Live Support project should display the following sections: Project, Issues, Activity, Sprints, Performance, Bugasura AI, and Project Settings. | Bugasura Live Support project displays the following sections: Project, Issues, Activity, Sprints, Performance, Bugasura AI, and Project Settings. |  | Pass
TC_DF_002 | TS_002 Project Functionality | Verify that users can filter issues by status from the issues page. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar 4.Navigate to the issue . 5.Navigate to the issues list page. 6.Apply the filter to display only "Open" issues. | Not Applicable | Only issues with the "Open" status should be displayed. | Only issues with the "Open" status are displayed. |  | Pass
TC_DF_003 | TS_002 Project Functionality | Verify that the issue details page loads successfully. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar 4.Navigate to the issue 5.Ensure you are logged in and authorized to view the issue. | Search : Bugasura Live Support | Issue details page should load without errors, displaying the issue’s title, description, status, assignee, and related information. | Issue details page loads without errors, displaying the issue’s title, description, status, assignee, and related information. |  | Pass
TC_DF_004 | TS_002 Project Functionality | Verify that users can edit issue details. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar 4.Navigate to the issue section 5.Open the issue details page. 6.Click on the "Edit" button. 7.Modify the issue's title and description. 8.Click "Save." | "Updated issue description regarding the bug." | The issue's title and description should be successfully updated, and the changes should be reflected on the issue details page. | The issue's title and description is successfully updated, and the changes are reflected on the issue details page. |  | Pass
TC_DF_005 | TS_002 Project Functionality | Verify that users can delete an issue. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar 4.Navigate to the issue section 5.Open the issue details page. 6.Click on the "Delete" button. 7.Confirm the deletion. | Not Applicable | Issue should be deleted, and the user should be redirected to the issues list page with a confirmation message. | Issue are deleted, and the user are redirected to the issues list page with a confirmation message. |  | Pass
TC_DF_006 | TS_002 Project Functionality | Verify the roadmap of the activity | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Type the name of the existing project in the search bar 4.Navigate to the Activity section | Not Applicable | Activity traking should be displayed. | Activity traking is displayed. |  | Pass
TC_DF_007 | TS_002 Project Functionality | Verify the Sprint Section | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Click on Sprint Section 4. Click on Add Sprints 5. Enter Sprint Name, enter start date,end date, no. of days 6. Select Status 7. Create | Not Applicable | A sprint iteration should be created. | A sprint iteration is created in scheduled state.
TC_DF_008 | TS_002 Project Functionality | Verify that user can edit Sprint | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Click on Sprint Section 4.Click on edit 5. edit the sprint name 6. Fill the start date, end date, sprint duration,change the status to progress |  | 1.End date should not be earlier than the start date. 2. Sprint duration days count should be in between the start date and end date. | 1. System is not acccepting end date earlier than start date. 2. System is accepting Sprint duration less than the / greater than the given time frame. |  | Fail
TC_DF_009 | TS_002 Project Functionality | Verify Bugasura AI section | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Click on Bugasura AI 4.Drag and drop jpeg,.docx,.pdf format 5.Click on upload | not applicable | The file should be uploaded only in .txt, docs or pdf format | File in only in .txt, docs or pdf format are uploaded. |  | Pass
TC_DF_010 | TS_002 Project Functionality | Verify Project detail | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Navigate to Projects setting 4.Rename the issue prefix under project detail 5.Save the detail | not applicable | User should be able to change the prefix and the changes should reflect everywhere(e.g. issues) | User is able to change the prefix and the related changes are reflecting everywhere.
TC_DF_011 | TS_002 Project Functionality | Verify Issue Fields | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Navigate to Projects setting 4.Click + icon under issue fields 5. select any type of field 6. Provide field name 7. Expand additional options 8.Save | not applicable | User should be able to add the new field | User is able to add the field after minimising all the expanded components. |  | Fail
TC_DF_012 | TS_002 Project Functionality | Verify Integration details | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Navigate to Projects setting 4.Navigate to integrations 5.Connect to any of the available apps (e.g., slack) | not applicable | User should be able to connect to the app and the same should be notified in the connected app. | User is able to connect to the app and the same is notified in the connected app. |  | Pass
TC_DF_013 | TS_002 Project Functionality | Verify Integration details | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Navigate to Projects setting 4.Navigate to integrations 5.Disconnect the App(slack) | not applicable | User should be disconnect from the app and the same should be notified in the connected app. | User is disconnect from the app and the same wasn't notified in the connected app. |  | Fail
TC_DF_014 | TS_002 Project Functionality | Verify Restart tour of Project | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2. click on restart tour 3. click next till tour ends | not applicable | User should be able to take the tour for all the sections | Restart tour is not working on all sections. |  | Fail

## Whats New
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
TC_DF_001 | TS_003 What's New Functionality | Validate "What's New" feature | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the What's New icon | Not Applicable | 1.Each release should display a "Read More" option. 2.The thumbnails for all releases should be uniform in size. 3.Clicking on any release thumbnail should redirect the user to the detailed description of the new feature. | 1."Introducing Bugasura's on-premise solution" release does not displays a "Read More" option. 2.The thumbnails for "Introducing Bugasura's on-premise solution" releases doesnot have a uniform size. 3.Clicking on "Introducing Bugasura's on-premise solution" release thumbnail doesnot redirects the user to the detailed description of the new feature. |  | Fail

## Manage
Test Case ID | Test Scenario | Test Case Title | Pre-requisites | Test Steps | Test Data | Expected Result (ER) | Actual Result | Priority | Result | Comments
TC_MF_001 | TS_004 Manage Functionality | Verify that a user can add a new team. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the "Teams" section. 2.Click the "Add Team" button. 3.Enter a valid team name 4.Click "Save." | Not Applicable | The new team should appear in the list of teams, and the details should be correctly saved. | The new team should appear in the list of teams, and the details should be correctly saved. |  | Pass
TC_MF_002 | TS_004 Manage Functionality | Verify that a user can edit an existing team | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Teams" section. Select an existing team from the list. Click "Edit." Modify the team name and description. Click "Save." | Not Applicable | The team details should be updated, and changes should be reflected in the list. | Changes are updated and reflecting in the section |  | Pass
TC_MF_003 | TS_004 Manage Functionality | verify that a member can be added | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Teams" section. Select an existing team from the list. Click on "invite Member" Invite a team member using email Click "Save." Repeat previous steps and add upto 5 more member click "Save" | Not Applicable | 1. The team member should receive an email 2. in case of free license user should not be allowed to add more than 5 users | 1.Invitee received an email 2. For free license admin is not able to send invite for more than allocated license |  | Pass
TC_MF_004 | TS_004 Manage Functionality | Delete a Team | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Teams" section. Select a team and remove members. Navigate back to team selection Select a team to delete. Click "Delete." Confirm the deletion. | Not Applicable | The Members should be removed from the list. The team should be removed from the list | The Members is removed from the list. The team is removed from the list |  | Pass
TC_MF_005 | TS_004 Manage Functionality | Verify that a user can create a new workflow. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Workflows" section in project settings Click the "Add status" button. Enter a name for the workflow. Define the stages and transitions. Click "Save." | Not Applicable | The new workflow should appear in the list with the correct stages and transitions. | 1. New worklfow appeared in the list and correct stages |  | Pass | Since the workflow has been relocated under project section , testing is covered from project setting view
TC_MF_006 | TS_004 Manage Functionality | Verify that a user can edit the stages of an existing workflow. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Workflows" section. Select an existing workflow. Click "Edit." Modify the stages and transitions. Click "Save." | Not Applicable | The workflow stages should be updated, and changes should be reflected in the list. | Workflow stages is modfied by drag and drop |  | Pass
TC_MF_007 | TS_004 Manage Functionality | Verify that a user can delete a workflow. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Workflows" section. Select a workflow to delete. Click "Delete." Confirm the deletion. | Not Applicable | The workflow should be removed from the list, and any associated data should be handled appropriately. | New workflow is deleted |  | Pass
TC_MF_009 | TS_004 Manage Functionality | Verify that a user can enable an existing module. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Modules" section. Select an existing module. Click "Enable." | Not Applicable | The module details should been enabled | User is able to enable the module, but landed back to home page |  | Fail
TC_MF_010 | TS_004 Manage Functionality | Verify that a user can disable a module. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Navigate to the "Modules" section. Select a module to disable. Click "disable." | Not Applicable | The module should be removed from the list, and any associated data should be handled appropriately. | User is able to disable the module, but landed back to home page |  | Fail
TC_MF_011 | TS_004 Manage Functionality | Verify that Restart Tour works in all module | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1. Login into the account 2. Navigate to the Manage icon. 3. Navigate to module. 4. clik on restart tour | Not Applicable | User should be able to see the tour of each module | The restart tour only responds on Teams section |  | Fail

## Bug Report
Project Name | Bugasura
Document | Bug Report
Reference Documents | Application Url
Reported By | Huma Sinha
Date of Creation | 12th Sep, 2024
Date of Review
Bug_Id | Priority | Description_Bug_Summary | Pre condition | Steps to Reproduce | Expected Result | Actual Result | Status | Browser | Screenshot
BG_001 | P4 | "Restart Tour" button does not respond when clicked after logging into the account, navigating to the Manage icon, and selecting a module. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the Manage icon. Select the desired module. Click on the "Restart Tour" button. | Tour should restart and guide the user through the module again. | The "Restart Tour" button does not respond or initiate the tour restart. |  | Google Chrome
BG_002 | P4 | The "Restart Tour" button is unresponsive or does not work as expected when the user navigates from a module to the Projects section after clicking "Restart Tour." | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the Manage icon. Select a module. Click on the "Restart Tour" button. Navigate to the Projects section. | The "Restart Tour" button should restart the tour within the module and properly reset when navigating to the Projects section. | If the tour restarts correctly when navigating to the Projects section, the issue still persists, indicating that the problem remains unresolved or affects the functionality. |  | Google Chrome |  | The Restart tour for previous section clicks, responds when navigated on the other sections.
BG_003 | P3 | Changes made to a module (e.g., enabling or disabling) persist even after the user navigates back to the dashboard page, leading to unexpected behavior. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the Manage icon. Select a module. Click on any module to view its details. Disable or enable the module. Route back to the dashboard page. | The changes made to the module should be applied as intended, but navigating back to the dashboard should reflect the updated state or settings accurately. | The state changes (enabling or disabling) made to the module persist even after navigating back to the dashboard, which indicates the issue might not be correctly reflected or reverted as expected. |  | Google Chrome
BG_004 | P2 | The "Read More" hyperlink is missing from the first thumbnail titled "Introducing Bugasura's On-Premise Solution" under the "What's New" section, which prevents users from accessing additional information. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the "What's New" section. Observe the first thumbnail titled "Introducing Bugasura's On-Premise Solution." | The "Read More" hyperlink should be present and functional, allowing users to click and view additional details about the thumbnail content. | The "Read More" hyperlink is missing from the first thumbnail, and users are unable to access more information. |  | Google Chrome
BG_005 | P4 | The image size varies inconsistently when expanding thumbnails in the "What's New" section. Specifically, the size of the image for the thumbnail titled "Introducing Bugasura's On-Premise Solution" differs from the sizes of images for other thumbnails. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the "What's New" section. Click on the expand image icon for the first thumbnail titled "Introducing Bugasura's On-Premise Solution." Observe the size of the expanded image. Repeat step 3 for other thumbnails in the "What's New" section. Observe the size of each expanded image. | All expanded images should have a consistent size across different thumbnails. | The size of the expanded image for the first thumbnail is different from the sizes of images for other thumbnails, indicating inconsistency in image display. |  | Google Chrome
BG_006 | P2 | Page fails to load visibility for the user in the browsers, causing confusion if the page is loading or stuck and ends up in multiple click | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to the Projects section and select a project. Click on "Bugasura AI" under the selected project. Observe that the page fails to load visibility, leading to multiple clicks or attempts to view the content. | The "Bugasura AI" page should be visibile to page loading as in all other components | The page does not load visibility and causing slowness in response |  | Google Chrome/ Windows
BG_007 | P1 | When clicking the "Bugasura AI" button multiple times in quick succession under the Projects section, the popup window exhibits a delay in response. Each click opens a new popup window, and closing these windows with the "X" button results in a black screen. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | Log into the account. Navigate to Bugasura AI under the Projects section after selecting a project. Click on the "Bugasura AI" button 4-5 times in quick succession. Observe that the popup windows respond with a delay, and each click opens a new popup window. Close the popup windows using the "X" button. | The "Bugasura AI" popup window should respond promptly to user clicks, For multiple click also one screen should open. . Closing the window should return the user to the previous view without displaying a black screen. | Each click opens a new popup window with noticeable delays in response. Closing the windows with the "X" button leads to a black screen. |  | Google Chrome
BG_008 | P4 | After logging into the account and navigating to the Projects icon, the user attempts to add a new custom field by clicking the + icon under Issue Fields in Project Settings. Once the user selects a field type, provides a field name, and expands additional options, the Save button overlaps with the Chatbot icon. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Navigate to Projects setting 4.Click + icon under issue fields 5. select any type of field 6. Provide field name 7. Expand additional options 8.If the save button and chatbot icon overlaps with each other and user is unable to save then issue persists | The new custom field should be saved successfully and listed under the issue fields section. | User is unable to save without collapsing the additional options. |  | Google Chrome
BG_009 | P4 | Logo is non-clickable on API & Docs page and differs in appearance from other pages. | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Navigate to the login page. 2. Click on Features 3.Navigate to API & Docs 4.Try clicking the Bugasura Logo. | User should be redirected to the home page. | User is unable to get to the homepage by clicking on the logo.
BG_010 | P3 | Inaccurate calculation for sprint duration | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Click on Sprint Section 4.Click on edit 5.Fill the start date, end date 6.Sprint duration should be lesser than the start date and end date timeline. | Sprint duration should be equal to the interval btw the start date and end date. | Sprint duration value is accepted as 0,1etc which is less than the interval. |  | Google chrome
BG_011 | P4 | Incorrect verbiage | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to the Projects icon 3.Click on Sprint Section 4.Click on edit | The label should be marked as Edit Sprint | The label is marked as rename sprint. |  | Google chrome
BG_012 | P4 | Conflicting plan details | Open the Application URL (ttps://my.bugasura.io/?go=log_in) in any supported Browser | 1.Login into the account 2.Navigate to My Profile 3. Navigate to Subscription 4. Observe the label of the free subscription plan. | The label should align with the footer of the subscription plan. | The label says Free Forever but mentions an expiry date at the footer of the free subscription plan box. |  | Google chrome

## Test Metrics
Test Metrics
No. of Requirements | 4
Avg. No. Of Test Cases written Per Requirement | 4
Total no. of Test Cases written for all | 42
Total no. of Test Cases executed | 42
No. Of Test Cases Passed | 31
No. Of Test Cases Failed | 11
No. Of Test Cases Blocked | 0
No. Of Test Cases Un Executed | 0
Total No. of Defects Identified | 12
Critical Defects Count | 1
Higher Defects Count | 2
Medium Defects Count | 3
Low Defects Count | 7
Customer Defects | 0
No. of Defects found in UAT | 0
Test Metrics
% of Test cases Executed | 100
% of Test cases Not Executed | 0
% of Test cases Passed | 73.8
% of Test cases blocked | 0